Design and Implementation of a Context-Aware Tourist Guide System Incorporating Machine Learning Recommendations and Generative AI

Project Management and Risks

10.1 Repository and Task Tracking

| Item | Details |
| --- | --- |
| Repository | https://github.com/Meirzhan1/geoguide-diploma (reviewed by the supervisor; committee access to be confirmed) |
| Task tracker | https://meirzhan.youtrack.cloud/projects/GEO, Scrum project, key GEO, one-week sprints |
| Branches | main is the reviewed baseline; work in branches named GEO-<number>-<description>. |
| Pull requests | Each request explains the change, references the task and describes how it was checked; the other team member reviews before merging. |
| Commits | Message form "GEO-<number>: description"; documentation and design changes are committed like code. |
| Submission tags | pre-defense-1, pre-defense-2, final-pre-defense; tags are not moved. |
| Secrets | Never committed; configuration examples with placeholders. |

10.2 Roles and Responsibilities

Both students are full-stack developers; each work item has one responsible student and a reviewer from the other. Ownership is in Chapter 1 (Table 1.3). The supervisor, Alua Myrzakerimova, reviews key deliverables at weekly meetings and the review comments are recorded in Section 10.7.

10.3 Backlog for the First Pre-Defense

Table 10.1 Initial tasks

| Task | Deliverable | Priority | Responsible | Due | Status |
| --- | --- | --- | --- | --- | --- |
| GEO-1 | Repository structure, .gitignore, configuration examples | High | Meirzhan | 19 Oct | Done |
| GEO-2 | README (title, problem, users, team, scope, technologies, links) | High | Beknazar | 19 Oct | Done |
| GEO-3 | Interview guide and invitations | High | Meirzhan | 19 Oct | Done |
| GEO-4 | Interviews (3) and findings | High | Both | 20–22 Oct | Done |
| GEO-5 | Project proposal | High | Meirzhan | 20 Oct | Done |
| GEO-6 | Literature review (at least 12 sources, 8 scientific) | High | Beknazar | 22 Oct | Done |
| GEO-7 | Existing system comparison | High | Meirzhan | 21 Oct | Done |
| GEO-8 | Technology comparison | High | Beknazar | 21 Oct | Done |
| GEO-9 | Requirements with acceptance criteria | High | Meirzhan | 21 Oct | Done |
| GEO-10 | Diagrams: context, use case, component (sources and exports) | High | Beknazar | 22 Oct | Done |
| GEO-11 | Clickable HTML interface prototype and screenshots, corrected to the requirements | High | Meirzhan | 22 Oct | Done |
| GEO-12 | Verification and evaluation plan | High | Beknazar | 22 Oct | Done |
| GEO-13 | Supervisor review and revisions | High | Both | 22–23 Oct | Done |
| GEO-14 | Risks and dependencies | Medium | Meirzhan | 23 Oct | Done |
| GEO-15 | Repository check and tag pre-defense-1 | High | Beknazar | 24 Oct | Done |
| GEO-16 | Presentation for the pre-defense | High | Both | 23 Oct | Done |

Task identifiers must match those in YouTrack; each task has an expected outcome, acceptance criteria and a link to its pull request.

10.4 Milestones

| No. | Milestone | Date |
| --- | --- | --- |
| M1 | First pre-defense: analysis, design, planning, prototype, evaluation plan | 24 October 2026 |
| M2 | Pilot objects fixed; knowledge base and reference photographs collected | 7 November 2026 |
| M3 | Recognition module with baseline comparison | 5 December 2026 |
| M4 | AI guide with retrieval and refusal; first answer evaluation | 26 December 2026 |
| M5 | Notifications and recommendations; integrated prototype | 23 January 2027 |
| M6 | Evaluation complete; final report and demonstration | Before the final pre-defense (date set by the programme) |

10.5 Risk Register

Probability (P) and impact (I) are rated low (L), medium (M) or high (H). The register is reviewed at each sprint planning meeting.

Table 10.2 Risks

| ID | Risk | P | I | Mitigation | Owner | Early warning |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Recognition confuses similar buildings or fails in poor light. | M | H | GPS candidate filtering; calibrated threshold; more reference photographs; fallback to chat and search; honest reporting of per-object results. | Beknazar | Top-1 accuracy below target on the first test set. |
| R2 | The AI guide gives unsupported or wrong statements. | H | H | Answer only from retrieved passages; refusal path; source labels; frozen test questions with human review; report incorrect-answer button. | Meirzhan | Faithfulness below target in the first evaluation. |
| R3 | Background geofencing is late or missed because of operating-system limits. | M | H | Test early on physical devices with a development build; nearest-places set within platform limits; radius ≥ 100 m; foreground fallback; report measured latency. | Beknazar | Trigger rate or delay worse than platform documentation. |
| R4 | Preparing verified content for the pilot objects takes more time than planned. | H | M | Limit the pilot to 12 objects; passage template with source fields; split the objects between students; Must items first. | Both | Fewer than half of the passages written by the milestone date. |
| R4b | Reference photographs of remote objects (Charyn, Kolsai, Kaindy, Bozzhyra) cannot be collected in time or have unclear reuse rights. | M | H | Use own photographs only; plan one field trip in Almaty Region; for objects that cannot be visited use photographs with an open licence and record the licence; the recognition test set may cover fewer objects, stated in the report. | Both | No reference photographs for a remote object by the end of Sprint 2. |
| R5 | Language-model provider is unavailable, too costly or restricted. | M | M | Provider-neutral interface; budget limit; recorded responses for tests; test an alternative provider or self-hosted model. | Meirzhan | Failed requests or cost alerts during development. |
| R6 | Privacy or consent problems with photographs, location or interviews. | L | H | Do not store photographs by default; no location history; consent wording in interviews and tests; privacy text matches behaviour. | Meirzhan | Any plan to store personal data. |
| R7 | Two-person team runs short of time (other courses). | H | M | Weekly sprints; MoSCoW priorities; buffer before each pre-defense; cut Could items first. | Both | Sprint goals missed twice in a row. |
| R8 | Interview evidence is thin or contradicts assumptions. | M | M | Schedule interviews immediately; use a short format; separate verified findings from assumptions; revise requirements. | Both | Fewer than three interviews two days before the pre-defense. |
| R9 | Copyright or licence problems with photographs and texts. | M | M | Use own photographs; write own summaries with cited sources; check licences of any imported images. | Meirzhan | Content copied without a source or licence. |
| R10 | iOS testing is not possible (device or developer account). | M | L | Develop and test on Android first; treat iOS as Could; state the limitation in results. | Beknazar | No iOS device available by the first sprint. |
| R11 | External service changes (recognition API quotas, model versions). | M | L | Use external recognition only for the baseline; store results; record model identifiers. | Beknazar | API errors or changed behaviour between runs. |
| R12 | Work is not traceable (large uncontrolled commits). | L | M | Small tasks; pull requests with review; commits reference GEO tasks. | Both | Commits without task identifiers. |

10.6 Dependencies

| Dependency | Needed for | Status |
| --- | --- | --- |
| List of pilot objects | Knowledge base, reference photographs, evaluation | Fixed: 12 objects (Chapter 1) |
| Physical Android device (and iOS if possible) | Geofencing and camera tests | Team devices; to be confirmed in Sprint 1 |
| Language-model access | AI guide | Provider selected in Sprint 3 |
| Interview participants and consent | Evidence of relevance | Done: three interviews held 20–23 October 2026 (Chapter 2) |
| Supervisor review | Feedback on deliverables | Weekly meetings |
| YouTrack and repository access for supervisor and committee | Traceability | Supervisor has reviewed the repository (Section 10.7); committee access to be confirmed |

10.7 Supervisor Feedback Log

Each review is recorded with the deliverable, the comment, the decision and the resulting change, so that it is visible whether the review led to improvements.

Table 10.3 Supervisor feedback

| Date | Deliverable | Supervisor comment | Decision / action | Result (task, commit) |
| --- | --- | --- | --- | --- |
| 23.10.2026 | Repository & GEO-1 – GEO-12 | The repository structure is well organized, and requirements and documentation are detailed. The interface prototype clearly reflects use cases. | Approve current project artifacts; proceed with sprint plan. | GEO-1 – GEO-12, commits in main |
| 23.10.2026 | GEO-14, GEO-16 | Risk register is thoroughly elaborated, and the pre-defense pdf is logically structured. | Include presentation in pre-defense materials, focusing on metrics and architecture. | GEO-14, GEO-16, tag pre-defense-1 (GEO-15) |
| 23.10.2026 | Next milestone plan (M2) | It is necessary to start collecting reference and test photographs for pilot objects on time and test geolocation on real devices. | Early geofencing testing (risk R3) during the next sprint. | Milestone M2 tasks |

10.8 Next Steps After the First Pre-Defense

- Start collecting reference and test photographs (M2).

- Implement the knowledge-base import tool and the recognition baseline (M3).

- Freeze evaluation question sets before tuning the AI guide (M4).

- Test geofencing on a physical device early in the next sprint (R3).